## Slide 1: Senoia Comprehensive Plan 2021-2041 Update
Kick-off - Public Hearing
February 2021

## Slide 2: Why a Comprehensive Plan?
State Law – Georgia Planning Act of 1989
Assess existing conditions and future needs
Establish community-based, long-term vision for the community’s future
Establish policy guidance for future actions based on a shared vision
Formalize plan to leverage public and private investment
Meet state planning requirements and maintain QLG status.
Remain eligible for grants and other funding programs.

## Slide 3: Plan Framework
Community Goals
Needs & Opportunities
Community Work Program
Land Use
Broadband
Vision Statement
Goals
Policies
Community Priorities
Five-year action plan
Long term and ongoing activities
-Character Areas
and Land Use
Narrative
Broadband goals

## Slide 4: Planning Horizon
20 years
5 year work program
5 year required plan update and also to be updated regularly to account for changes in city, economy, and environment
5-year Work Program
20 year Vision
2021
2026
2041

## Slide 5: Comprehensive Plan Team
City Staff
Consultant Team-TRRC
Steering Committee
The Public
Elected Officials

## Slide 6: Public Participation
Activities include:
  Steering Committee – Community Stakeholders
    Elected officials from each municipality
    Economic development representative
    Other community appointees
  Open House/Community Visioning Events
    Citizen and stakeholder input
    Community vision for the future
  Draft Plan Review
    30-day local and regional review

## Slide 7
 | Feb | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Task |  |  |  |  |  |  |  |  |  | 
Initial Kick off/1st public hearing | X |  |  |  |  |  |  |  |  | 
Steering Committee meetings |  | X | X | X | X | X |  |  |  | 
Public Open House |  |  |  | X |  |  |  |  |  | 
Comprehensive Plan Development |  |  | X | X | X | X | X |  |  | 
2nd public hearing/Letter of Transmittal for Review |  |  |  |  |  |  |  | X |  | 
Review by the RC and DCA |  |  |  |  |  |  |  |  | X | 
Adoption by Town |  |  |  |  |  |  |  |  |  | X
Proposed Schedule for Completion of the Senoia Comprehensive Plan 2021-2041

## Slide 8
Kimberly Dutton
Planner
Three Rivers Regional Commission
770-854-6026
ksdutton@threeriversrc.com
Questions???